## Breakdown
Acceptance Test | Task ID | Task Description | Task Points | Started | Expected | Completed | Removed
AT:18.1 | T:18.1.1 | Create the "editing the date" UI
| T:18.1.2 | Create a new election object with the date we want (a future date)
AT:18.2 | T:18.2.1 | Create the "editing the date" UI
| T:18.1.2 | Create a new election object with the date we want (a past date)
AT:18.3 | T:18.3.1 | Create the "editing the date" UI
| T:18.3.2 | Use an existing election object and change its date
AT:3.1 | T:3.1.1 | Use an existing election object
| T:3.1.2 | Create an admin object and freeze the election
AT:3.2 | T:3.2.1 | Use an existing election object that we froze before
| T:3.2.2 | Create an admin object and freeze the election
AT:1.1 | T:1.1.1 | Create relevant abstract classes |  | 2019-02-19 |  | 2019-02-19
AT:1.1 | T:1.1.1 | Create tests for Election Class |  | 2019-02-20 |  | 2019-02-24
AT:1.1 | T:1.1.2 | Create tests for the Question Class |  | 2019-02-20 |  | 2019-02-24
AT:1.1 | T:1.1.3 | Create Election Class |  | 2019-02-20 |  | 2019-02-24
AT:1.1 | T:1.1.4 | Create the Question class |  | 2019-02-20 |  | 2019-02-24
AT:1.1 | T:1.1.5 | Integrate the Election and Question class with the Election creation UI |  | 2019-02-20 |  | 2019-02-24
AT:1.1 | T:1.1.6 | Create and wire up the Firestore |  | 2019-02-23 |  | 2019-02-24
AT:1.1 | T:1.1.7 | Integrate Firestore with the Election creation UI |  | 2019-02-23 |  | 2019-02-24

## Task Count
Interval Start | Interval End | Tasks Done | Cumulative Completed | Total Tasks