## Breakdown
Acceptance Test | Task ID | Task Description | Task Points | Started | Expected | Completed | Removed
AT:18.1 | T:18.1.1 | Create the "editing the date" UI | 1 | 2019-02-15 | 2019-02-15 | 2019-02-15
| T:18.1.2 | Create a new election object with the date we want (a future date) | 2 | 2019-02-20 | 2019-02-21 | 2019-02-23
AT:18.2 | T:18.2.1 | Create the "editing the date" UI | 1 | 2019-02-15 | 2019-02-15 | 2019-02-15
| T:18.1.2 | Create a new election object with the date we want (a past date) |  | 2019-02-20 | 2019-02-21 | 2019-02-23
AT:18.3 | T:18.3.1 | Create the "editing the date" UI | 1 | 2019-02-15 | 2019-02-15 | 2019-02-15
| T:18.3.2 | Use an existing election object and change its date | 1 | 2019-02-20 | 2019-02-21 | 2019-02-23
AT:3.1 | T:3.1.1 | Use an existing election object | 1 |  |  |  | 2019-02-23
| T:3.1.2 | Create an admin object and freeze the election | 2 | 2019-02-20 | 2019-02-21 | 2019-02-23
AT:3.2 | T:3.2.1 | Use an existing election object that we froze before | 1 | 2019-02-20 | 2019-02-24 |  | 2019-02-23
| T:3.2.2 | Create an admin object and freeze the election | 2 | 2019-02-20 | 2019-02-24 |  | 2019-02-23
AT:1.1 | T:1.1.1 | Create the main UI | 1 | 2019-02-15 | 2019-02-15 | 2019-02-15
| T:1.1.2 | Create the election creation UI | 1 | 2019-02-15 | 2019-02-15 | 2019-02-15
| T:1.1.3 | Create the election object | 2 | 2019-02-19 | 2019-02-21 | 2019-02-20
| T:1.1.4 | Create relevant abstract classes | 2 | 2019-02-19 | 2019-02-24 | 2019-02-19
| T:1.1.5 | Create tests for Election Class | 2 | 2019-02-20 | 2019-02-24 | 2019-02-19
| T:1.1.6 | Create tests for the Question Class | 2 | 2019-02-20 | 2019-02-24 | 2019-02-19
| T:1.1.7 | Create Election Class | 2 | 2019-02-20 | 2019-02-21 | 2019-02-22
| T:1.1.8 | Create the Question class | 2 | 2019-02-20 | 2019-02-24 | 2019-02-22
| T:1.1.9 | Integrate the Election and Question class with the Election creation UI | 2 | 2019-02-20 | 2019-02-24 | 2019-02-24
| T:1.1.10 | Create and wire up the Firestore | 2 | 2019-02-23 | 2019-02-24 | 2019-02-24
| T:1.1.11 | Integrate Firestore with the Election creation UI | 2 | 2019-02-23 | 2019-02-24 | 2019-02-24

## Breakdown - Iteration 2
Acceptance Test | Task ID | Task Description | Task Points | Started | Expected | Completed | Removed | Pairs
AT:20.1 | T:20.1.1 | Create the "Done" Voting Button | 1 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.1.2 | Extract the database for the election | 2 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.1.3 | Evaluate the database (check the votes for each question is incremented by one) | 2 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.1.4 | Evaluate each option on its own that the votes are incremented properly | 2 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.1.5 | Create an entirely new interface to allow voting for multiple questions dynamically | 1 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK, SD
| T:20.1.6 | Extract user input for election | 2 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK,SD
| T:20.1.7 | Evaluate the database (check that the votes were incremented) | 2 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK,SD
| T:20.1.8 | Evaluate each option to ensure that the vote incrementation is completed properly | 2 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK,SD
AT:20.2 | T:20.2.1 | Create the "Cancel" button in the election process | 1 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.2.2 | Extract the database for the election | 2 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.2.3 | Evaluate the database (check that nothing has changed) | 2 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.2.4 | Evaluate each option on its own that the votes did not change | 2 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.2.5 | Created entirely new interface for election process, created new "cancel" | 1 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK, SD
| T:20.2.6 | Extract the database for the election for new interface | 2 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK,SD
| T:20.2.7 | Evaluate the database (check that nothing has changed) in new interface | 2 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK,SD
| T:20.2.8 | Evaluate each option on its own that the votes did not change following new interface implementation | 2 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK,SD
AT:20.3 | T:20.3.1 | Create a handler that closes the app | 2 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.3.2 | Extract the database for the election | 2 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.3.3 | Evaluate the database (check that nothing has changed) | 2 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.3.4 | Evaluate each option on its own that the votes did not change | 2 | 2019-03-01 | 2019-03-11 | 2019-03-01 |  | SD, HA
| T:20.3.1 | Create a handler that closes the app in new interface | 1 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK, SD
| T:20.3.2 | Extract the database for the election for new interface | 2 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK,SD
| T:20.3.3 | Evaluate the database (check that nothing has changed) in new interface | 2 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK,SD
| T:20.3.4 | Evaluate each option on its own that the votes did not change following new interface implementation | 2 | 2019-03-10 | 2019-03-17 | 2019-03-17 |  | AK,SD
AT:5.1 | T:5.1.1 | Create the "View Elections" Button on the admin page | 3 | 2019-03-09 | 2019-03-12 | 2019-03-09 |  | LH, AS
| T:5.1.2 | Create and set up the recycler view | 3 | 2019-03-09 | 2019-03-12 | 2019-03-10 |  | LH, AS
| T:5.1.3 | Set up the FireStore recycler adapter | 3 | 2019-03-09 | 2019-03-12 | 2019-03-10 |  | LH, AS
| T:5.1.4 | Make the view holder | 3 | 2019-03-09 | 2019-03-12 | 2019-03-09 |  | LH, AS
AT:2.1 | T:2.1.1 | Create the "Details" Button for the Election list page | 1 | 2019-03-16 | 2019-03-16 | 2019-03-16 |  | HA,AA
| T:2.1.2 | Extract the election from the database | 2 | 2019-03-03 | 2019-03-10 | 2019-03-03 |  | LH, AK
| T:2.1.3 | Create a text field to hold the number of votes | 1 | 2019-03-03 | 2019-03-10 | 2019-03-03 |  | LH, AK
| T:2.1.4 | Connect the text field to the number of votes. | 2 | 2019-03-03 | 2019-03-10 | 2019-03-03 |  | LH, AK
AT:2.2 | T:2.2.1 | Create the "Details" Button for the question page | 1 | 2019-03-11 | 2019-03-17 | 2019-03-16 |  | LH, AK
| T:2.2.2 | Extract the question from the election object | 2 | 2019-03-03 | 2019-03-10 | 2019-03-03 |  | LH, AK
| T:2.2.3 | Create a text field to hold most-selected option | 1 | 2019-03-11 | 2019-03-17 | 2019-03-16 |  | LH, AK
| T:2.2.4 | Get the most selected option and view it in the text field. | 2 | 2019-03-03 | 2019-03-10 | 2019-03-03 |  | LH, AK
AT:2.3 | T:2.3.1 | Create the "Details" Button for the options | 1 | 2019-03-11 | 2019-03-17 | 2019-03-16 |  | LH, AK
| T:2.2.2 | Extract the options from the question | 2 | 2019-03-03 | 2019-03-10 | 2019-03-03 |  | LH, AK
| T:2.2.3 | Create a text field to number of votes per option | 1 | 2019-03-11 | 2019-03-17 | 2019-03-16 |  | LH, AK
| T:2.2.4 | Get the number of votes per option and view it in the text field. | 2 | 2019-03-03 | 2019-03-10 | 2019-03-03 |  | LH, AK
AT:22.1 | T:22.1.1 | Create the "View Results" button | 1 | 2019-03-16 | 2019-03-16 | 2019-03-16 |  | HA,AA
| T:22.1.2 | Wire up the "View Results" button to view results activity (US 2) | 2 | 2019-03-16 | 2019-03-16 | 2019-03-16 |  | LH, AK

## Breakdown - Iteration 3
Acceptance Test | Task ID | Task Description | Task Points | Started | Expected | Completed | Removed | Pairs
7.1 | 7.1.1 | Add a text field the holds the title "total number of votes" | 0.5 | 2019-04-01 | 2019-04-03 | 2019-04-01 |  | HA,SM
| 7.1.2 | Add a text field that holds the number of votes | 0.5 | 2019-04-01 | 2019-04-03 | 2019-04-01 |  | HA,SM
| 7.1.3 | connect the total number of fields to actual number by creating a method to count | 0.5 | 2019-04-01 | 2019-04-03 | 2019-04-01 |  | HA,SM
8.1 | 8.1.1 | Add a text field the holds the title "total number of votes" | 0.5 | 2019-04-01 | 2019-04-03 | 2019-04-01 |  | HA,SM
| 8.1.2 | Add a text field that holds the number of votes | 0.5 | 2019-04-01 | 2019-04-03 | 2019-04-01 |  | HA,SM
| 8.1.3 | connect the total number of fields to actual number by creating a method to count | 0.5 | 2019-04-01 | 2019-04-03 | 2019-04-01 |  | HA,SM
17.1 | 17.1.1 | Create an error page UI with all the proper buttons and fields | 1 | 2019-03-23 | 2019-03-29 | 2019-03-27 |  | HA,AK
|  | Create a connection between the error page and getting back to the main page | 1 | 2019-03-23 | 2019-03-29 | 2019-03-27 |  | HA,AK
|  | Create a method for chcking the dates properly | 1 | 2019-03-23 | 2019-03-29 | 2019-03-27 |  | HA,AK
|  | Create an election with an expired end date | 0.5 | 2019-03-23 | 2019-03-29 | 2019-03-27 |  | HA,AK
17.2 | 17.2.1 | Create an election that did not start yet, the start date is in the future | 0.5 | 2019-03-23 | 2019-03-29 | 2019-03-27 |  | HA,AK
17.3 | 17.3.1 | Create an election that is open and has proper dates | 0.5 | 2019-03-23 | 2019-03-29 | 2019-03-27 |  | HA,AK
17.4 | 17.4.1 | Create an election that is open and has proper dates and that was frozen by the admin | 0.5 | 2019-03-23 | 2019-03-29 | 2019-03-27 |  | HA,AK
9/10.1 | 9/10.1.1 | Created an interface for the user to build off of | 0.5 | 2019-03-29 | 2019-04-02 | 2019-03-29 |  | LH,AA
|  | Created a user class to hold the details for each user | 0.5 | 2019-03-29 | 2019-04-02 | 2019-03-29 |  | LH,AA
|  | Created a user manager class to handle actions like login, logout, employing the singleton pattern | 1.5 | 2019-04-01 | 2019-04-05 | 2019-04-07 |  | LH, JL
|  | created an activity to allow users to login | 1 | 2019-04-01 | 2019-04-05 | 2019-04-07 |  | LH, JL
|  | implemented the activity functions (login, logout, register, delete) | 2 | 2019-04-01 | 2019-04-05 | 2019-04-07 |  | LH, JL
|  | pull information for the login and check if its admin and redirect | 0.5 | 2019-04-01 | 2019-04-05 | 2019-04-07 |  | LH, JL
9/10.2 | 9/10.2.1 | pull information for the login and check if its student and redirect | 0.5 | 2019-04-01 | 2019-04-05 | 2019-04-07 |  | LH, JL
9/10.3 | 9/10.3.1 | pull information for the login and check if its user and dont redirect | 0.5 | 2019-04-01 | 2019-04-05 | 2019-04-07 |  | LH, JL

## Task Count
Interval Start | Interval End | Tasks Done | Cumulative Completed | Total Tasks